## Slide 1: eLearning Progress report – Sprint c
17/06/23
58/Diogo Magalhães, Gabriel Silva,
Ricardo Peixoto, Ricardo Venâncio e Vicente Teixeira

## Slide 2: agenda
Introduction
Completed Activities
System Objectives
Development Process
Critical Analysis of Results
Quality of the product
Sprint Retrospective
Self-Assessment

## Slide 3: INTRODUCTION
This report provides an overview of our achievements, challenges, and a retrospective of what was done. We'll discuss key milestones reached, obstacles encountered, and future improvements. We will review our accomplishments and continue working together towards our shared goals.

## Slide 4: Planning
The plan adopted by our team

## Slide 5: Completed Activities
ID | Description | Assigned | Baseline | Real | Status
US3004 | As User, I want to share a board | Gabriel Silva | Start: 01-06-23 End: 07-06-23 | Start: 07-06-23 End: 15-06-23 | 
US3005 | As User, I want to view, in real-time, the updates in the shared boards | Vicente Teixeira Ricardo Peixoto | Start: 25-05-23 End: 18-06-23 | Start: 05-06-23 End: 18-06-23 | 
US3006 | As User, I want to create a post-it on a board | Ricardo Venâncio | Start: 01-06-23 End: 07-06-23 | Start: 25-05-23 End: 03-05-23 | 
US3007 | As User, I want to change a post-it | Diogo Magalhães​ | Start: 29-05-23 End: 07-06-23 | Start: 09-06-23 End: 18-06-23 | 
US3008 | As User, I want to undo the last change in a post-it | Gabriel Silva | Start: 29-05-23 End: 07-06-23 | Start: 05-05-23 End: 18-06-23 | 

## Slide 6: Completed Activities
ID | Description | Assigned | Baseline | Real | Status
US3009 | As User, I want to view the history of updates on a board | Vicente Teixeira Ricardo Peixoto | Start: 29-05-23 End: 07-06-23 | Start: 07-06-23 End: 18-06-23 | 
US3010 | As User, I want to archive a board I own | Ricardo Venâncio | Start: 29-05-23 End: 18-06-23 | Start: 25-05-23 End: 05-06-23 | 
US2004 | As Student, I want to take an exam | Ricardo Venâncio Ricardo Peixoto Vicente Teixeira Gabriel Silva Diogo Magalhães | Start: 01-06-23 End: 07-06-23 | Start: 01-06-23 End: 18-06-23 | 
US2005 | As Student, I want to view a list of my grades | Gabriel Silva​ | Start: 29-05-23 End: 07-06-23 | Start: 09-06-23 End: 15-06-23 | 
US2006 | As Teacher, I want to view a list of the grades of exams of my courses | Ricardo Peixoto | Start: 29-05-23 End: 07-06-23 | Start: 05-05-23 End: 18-06-23 | 

## Slide 7: Completed Activities
ID | Description | Assigned | Baseline | Real | Status
US2009 | As Student, I want to take an automatic formative exam | Ricardo Venâncio Ricardo Peixoto Vicente Teixeira Gabriel Silva Diogo Magalhães | Start: 01-06-23 End: 07-06-23 | Start: 07-06-23 End: 18-06-23 | 
US4002 | As User, I want to cancel a meeting | Ricardo Venâncio | Start: 25-05-23 End: 31-05-23 | Start: 25-05-23 End: 31-05-23 | 
US4003 | As User, I want to accept or reject a meeting request | Ricardo Venâncio | Start: 25-05-23 End: 31-05-23 | Start: 25-05-23 End: 03-05-23 | 
US4004 | As User, I want to view a list of participants in my meeting and their status (accept or reject) | Ricardo Venâncio​ | Start: 25-05-23 End: 31-05-23 | Start: 25-05-23 End: 31-05-23 | 
US5002 | The presentation itself | Ricardo Venâncio Ricardo Peixoto Vicente Teixeira Gabriel Silva Diogo Magalhães | Start: 29-05-23 End: 18-06-23 | Start: 16-06-23 End: 18-06-23 | 

## Slide 8: System objectives
The functional objectives and non-functional objectives

## Slide 9: Functional objectives
Shared Boards
Users
Exams
Meetings
Courses

## Slide 10: Non-Functional objectives
Java
Persistence
Documentation
GitHub
Scripts
ANTLR
Server
Synchronization

## Slide 11: Development Process
What the team has adopted to achieve the results

## Slide 12: Development process
Product quality is assured
Results satisfy the client needs with proper documentation
DISCOVERY
Collect ideas from team members
Early risks understood
PLANNING
Defining size, priority, and difficulty
Assigning tasks to team members
DESIGN
Development Planned
Product Design with respective documentation
Building our features based on the previous phase
Product quality needs to meet design requirement
LAUNCH
DEVELOPMENT

## Slide 13: Critical analysis of results
Adopting the SWOT format

## Slide 14: Critical analysis of results
Weaknesses
Strengths
Opportunities
Threats
Ineffective communication or conflicts within the team
Poor time management
High motivation and commitment to achieving team goals.
Positive team dynamics
Competition from other groups
Unforeseen events
Training and development of professional and soft skills
Implementation of new tools/technologies

## Slide 15: Quality of the product
Results achieved by the team

## Slide 16: Quality of the final product
Product Performance
User Experience
Innovation
Quality & Testing
Gathering Feedback
Product Maintenance

## Slide 17: Sprint retrospective
Using the Starfish Method

## Slide 18: Self-assessment
Evaluation made by the team about the skills before and after the project

## Slide 19: Self-assessment
 | Before the project |  | After the project | 
 | Technical | Behavioral | Technical | Behavioral
Diogo Magalhães | Good | Good | Good | Good
Gabriel Silva | Good | Very Good | Very Good | Very Good
Ricardo Peixoto | Fair | Fair | Good | Good
Ricardo Venâncio | Good | Good | Good | Good
Vicente Teixeira | Good | Very Good | Very Good | Good
*scale consists of very weak, weak, fair, good, very good, excellent

## Slide 20: MEET OUR TEAM
Diogo Magalhães
Gabriel Silva
Ricardo Peixoto
Ricardo Venâncio
Vicente Teixeira

## Slide 21: THANK YOU
The Group 58